## Projects
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Project A | M1: Job A; M2: Job B; M3: Job C
Project B | M3: Job G; M4: Job K; M5: Job M
Project C | M4: Job H; M5: Job E; M6: Job G; M7: Job B; M8: Job E
Project D | M2: Job D; M3: Job F; M4: Job I; M5: Job H
Project E | M8: Job J; M9: Job A
Project F | M9: Job B; M10: Job C; M11: Job K
Project G | M5: Job L; M6: Job M; M7: Job E
Project H | M8: Job A; M9: Job B; M10: Job D; M11: Job I
Project I | M10: Job L; M11: Job F; M12: Job K

## Quotes
| Job A | Job B | Job C | Job D | Job E | Job F | Job G | Job H | Job I | Job J | Job K | Job L | Job M
Contractor A | 230 |  |  |  | 30 |  |  |  | 80 |  |  | 200
Contractor B | [10 empty] | 140 |  | 290
Contractor C | [6 empty] | 550 |  |  | 190
Contractor D |  |  |  | 450 | [7 empty] | 190
Contractor E |  | 130 |  |  | 20
Contractor F |  |  | 200 |  |  | 140
Contractor G | [6 empty] | 505 |  | 60
Contractor H | 300 |  |  | 400 |  |  |  | 120
Contractor I | [6 empty] | 600
Contractor J |  | 150 |  |  |  | 170 |  |  |  | 240
Contractor K |  |  | 150 |  |  |  |  | 140 |  |  | 150 |  | 300

## Dependencies
| Project A | Project B | Project C | Project D | Project E | Project F | Project G | Project H | Project I
Project A
Project B | x
Project C
Project D
Project E |  |  | x | x
Project F | [6 empty] | x
Project G |  | x
Project H
Project I |  |  |  |  | x

## Value
Value
Project A | 500
Project B | 300
Project C | 400
Project D | 1000
Project E | 2000
Project F | 100
Project G | 1500
Project H | 1000
Project I | 1000